## Gantt Chart
THE WONDEROUS AND PROPHETIC GANTT CHART OF THE GLORIOUS TECHNOCRATIC DICTATORSHIP OF TEAM 6
PROJECT TITLE |  | Voice Modulator |  |  |  |  | COMPANY NAME | [6 empty] | Team 6 | [15 empty] | Early
PROJECT MANAGER |  | Captain Hindsight |  |  |  |  | DATE | [6 empty] | 2018-10-07 | [15 empty] | Planned
Overran
Delayed
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | CONCEPTION | [6 empty] | PLANNING, RESEARCH | [6 empty] | DEVELOPMENT | [34 empty] | TESTING/DEBUGGING
[7 empty] | WEEK 1 (10/7) | [6 empty] | WEEK 2 (10/14) | [6 empty] | WEEK 3 (10/21) | [6 empty] | WEEK 4 (10/28) | [6 empty] | WEEK 5 (11/4) | [6 empty] | WEEK 6 (11/11) | [6 empty] | WEEK 7 (11/18) | [6 empty] | WEEK 8 (11/25) | [6 empty] | WEEK 9 (12/2)
[7 empty] | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S
1 | Project Conception
1.1 | Decide on Project | Group | 2018-10-07 | 2018-10-07 | 0 | 100% | bar: WEEK 1 (10/7) S to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
1.1.2 | Order parts | Group | 2018-10-07 | 2018-10-14 | 7 | 100% | bar: WEEK 1 (10/7) S to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
1.2 | Meeting Scheduling | Group | 2018-10-07 | 2018-10-07 | 0 | 100% | bar: WEEK 1 (10/7) S to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
2 | Project Definition, Planning, and Research
2.1 | Program chip using AVR Dragon | Jordan, Stephen | 2018-10-14 | 2018-10-21 | 8 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
2.2 | Research ATMEL Chip Capabilities and Settings | Group | 2018-10-14 | 2018-10-21 | 8 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
2.3 | Research DAC Capabilities and Settings | Philip, Stephen | 2018-10-14 | 2018-10-21 | 8 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
2.4 | Research ADC Capabilities and Settings | Aaron, Philip, Stephen | 2018-10-14 | 2018-10-21 | 8 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
3 | Project Development
3.1 | Prototype Circuit on Breadboard | Jordan, Stephen | 2018-10-21 | 2018-10-21 | 1 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
3.2 | Program Simple Throughput Test | Aaron, Philip, Stephen | 2018-10-22 | 2018-11-03 | 13 | 100% | bar: WEEK 1 (10/7) M to WEEK 9 (12/2) S
3.2.1 | Program SImple Voice Modulation | Aaron, Philip | 2018-11-04 | 2018-11-17 | 14 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) S; WEEK 7 (11/18) W to WEEK 9 (12/2) S
3.2.2 | Program Other/Better Modulation Programs | Aaron, Philip, Stephen | 2018-11-18 | 2018-11-24 | 7 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) S to WEEK 9 (12/2) S
3.3 | Create Board Schematic | Aaron, Ryan | 2018-10-24 | 2018-11-13 | 21 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 3 (10/21) W to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
3.3.1 | Create Board Layout | Aaron, Ryan | 2018-10-31 | 2018-11-13 | 14 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 4 (10/28) W to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
3.3.1.1 | Send Board Schematic To OSH Park | Ryan | 2018-11-14 | 2018-11-14 | 0 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) W; WEEK 7 (11/18) W to WEEK 9 (12/2) S
4 | Project Testing/Debugging
4.1 | Integrate Chip On Board | Group | 2018-11-21 | 2018-11-21 | 1 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
4.1.1 | Test Chip On Board | Group | 2018-11-23 | 2018-11-28 | 6 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) M
4.1.2 | Integrate DAC On Board | Group | 2018-11-21 | 2018-11-21 | 1 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
4.1.3 | Test DAC On Board | Group | 2018-11-23 | 2018-11-28 | 6 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) M
4.1.4 | Integrate ADC On Board | Group | 2018-11-21 | 2018-11-21 | 1 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
4.1.5 | Test ADC On Board | Group | 2018-11-23 | 2018-11-28 | 6 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) M
4.1.6 | Test Throughput Program | Group | 2018-11-28 | 2018-11-29 | 2 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S
4.1.7 | Test Voice Modulation Program | Group | 2018-11-30 | 2018-12-02 | 3 | 100% | bar: WEEK 1 (10/7) M to WEEK 3 (10/21) S; WEEK 5 (11/4) S to WEEK 6 (11/11) T; WEEK 7 (11/18) W to WEEK 9 (12/2) S